## Sheet1
Area | Current Situation (Where are you now?) | Desired State (Where do you want to be?) | Action Plan (How are we going to get there?) | Priority (High / Medium / Low) | Complete (Yes / No) | Notes
Infrastructure - Hardware (e.g. PC, dual screens, headset, monitor raisers, laptop for remote working, smart card readers, telephony system, mobile usage) | Single screen working for all staff which will be allocated for eHub working. | Dual screen working for all eHub staff | Order 12 new monitors that have capacity to work with the existing PCs/monitors with monitor raisers | Medium | No | Needed to be able to view Smart Inbox and clinical system at same time
| Only 4 hot desks available at site 1 for eHub working | to have 6 hot desks available | Order full IT and set up 2 additional hot desks | High | No | Needed to accommodate eHub team
Infrastructure - Software (e.g. VPN set up, Smart Inbox, NHS email, tool bar, back up NHS email set up, internal communication platform in place) | No staff have currently completed Smart Inbox training | For all staff to be trained on Smart Inbox and to have SI led eHub | To download the toolbar and book staff onto Smart Inbox training | High | No | Needs to be complete before going live
| Currently have a practice nhs.net email in place as the back up email address | To have a back up nhs.net email in place in case any eConsults fail to reach the Smart Inbox | To request to have this email address created as the eHub develops to a fully functioning hub with multiple sites | Low | No | The priority of this task will increase when more practices go live with eHub
| Currently use email as a means of internal communication | To have the whole team on the same communication “channel” | To set up a MS teams channel or an internal Whatsapp group to communicate internally | Medium | No | To decide what the preferred internal communication platform will be (not email)
| Currently have one VPN software set up across the estate | To have two different VPNs set up across the estate incase one fails | To request IT to set up another VPN software for the eHub | Medium | No | Need as part of contingency plan
People and Stakeholders (e.g. tech lead, eHub clinicians, eHub admin, Site Clinical, Site Admin, ARRS roles) | Currently have on site GP’s, admins roles and AMP role in place | To have eHub designated clinical admin leads in place and eHub GPs and admin staff in place | To allocate or recruit both an admin and clinical lead role for the eHub | High | No | This needs to be done ASAP in order to develop the eHub
| Currently do not a designated tech or IT lead in place to lead on eHub delivery | To have a designated tech/IT lead in place dedicated to eHub for requests around EMIS, hardware, software etc. | To allocate or recruit an IT/Tech lead for the eHub | High | No | This needs to be done ASAP in order for the eHub to develop and to have a designated person to fix any IT related issues
| Currently do not have a care navigator in place for eHub | To have a care navigator in post | To recruit a care navigator | Medium | No
Training Requirements (e.g. eConsult Training, eHub Training, Smart Inbox, Triage Training, Administator, Clinical) | All staff have only complete eConsult training | For practice staff to receive triage training (based on model) and for eHub staff to complete training | To book training once staff have been confirmed | Medium | No | Training will need to be completed once applicable staff are in post i.e. eHub admin lead etc.
| Currently no SOP or workflow agreed | To have an agreed SOP in place or at least a flow chart outlining how it will work with key contacts on it. | To have SOP or workflow in place and everyone knows what the process is | High | No | This needs to be tried and tested
Data Collection Tools (e.g. Clinical System, eConsult Data Reports, PT feedback reports, Clinical Audit) | Currently don’t run patient feedback reports as part of data collection | To run patient feedback reports regularly to scope how eHub is doing and how we can improve going forward | To develop a robust communication plan of when to send out reminders to push for patient feedback | Medium | No | Patient feedback reports is vital for the eHub moving forward - look at best practice to gather this data
| Have currently made a plan of what data needed to collect, when to collect it and by what means | To run tests to see if the data collection and reports are collecting the correct data that is needed | To set up a template and set up searches to see whether it provides the correct data collection that is needed | Medium | No | Tests are vital to ensure we are capturing the data that is necessary
Finance (e.g. budget for additional eHub staff i.e. clinical and admin, budget in place for additional infrastucture) | Currently do not have a budget agreed for the additional infrastructure (hardware) that is required | To have purchased all of the necessary infrastructure in enable a smooth running eHub | To create a business case for proposal of budget and secure the budget to make purchases | High | No | The hardware is needed to ensure smooth running of eHub
Business Continuity Plan (e.g. if EMIS goes down) | Currently no business continuity plan in place | To have a back up plan is EMIS goes down | To create business continuity plan and test it | High |  | Continuity plan to be drafted and approved ASAP