## Risks
RAID LOG
| Risk No. | Date Identified | Description | Department | Project | Probability | Impact | Impact on other projects | Preventative Actions | Contingent Actions | Owner | Actions by | Target Date | Status | Notes
i.e . | 1 | 04.11.2022 | There is a risk of delays due to internal capacity to deliver changes or tasks within the project | Transformation | Brocklebank PNC | Medium | High | ABC | Ensure appropriate project team is agreed and scoped prior to kick off | Use simple implementation and development plan as well as increase time to delivery or go live. | Project Manager | Project Manager | tbc | Open | n/a

## Actions
ACTIONS
Action No: | Date raised | Area | Priority | Description | Action by | Deadline | Progress | Status
1 | 01.11.2022 | Marketing | Medium | PCN operations lead to organise an engagement session with the PPG leads to discuss eHub project | Project Manager |  |  | Pending

## Issues
Issues
Issue No. | Priority | Description | Owner | Cause | Resolution | Status | Comments | Target date
1 | Medium | Not being able to divert eConsults for OOH | Tom Billers | No clear OOH functionality in place | Work around by having two URLs with custom hours | Pending | tbc | 01.12.2022

## Decisions
Decisions
Decision no: | Date made | Description | Impact | Approver/decision maker | Evidence e.g. Email date and title
1 | 01.11.2022 | Scope was agreed to deliver a secondary eHub for clinical only | More simple implementation with scope to grow but customer understands the cons with a secondary over primary eHub | Project Sponsor | email link

## RiskIssue levels
Risks
Field | Menu | Description
Probability | High | Very likely that this risk will occur/happen.
| Medium | 50/50 chance that this risk will occur.
| Low | Low probability that this risk will occur.
Impact | High | This would badly impact the project e.g. cost, delay, quality.
| Medium | A manageable impact on the project.
| Low | A low impact on the project.
Status | Open | In progress
| Pending | Waiting on action by another party
| Closed | Closed as agreed by customer/sponsor
Issues
Field | Menu | Description
Priority | High | This issue must be resolved for progress to be made.
| Medium | This impacts the project, but doesn’t stop progress.
| Low | A low impact on the project. Perhaps optional to fix.
Status | Open | In progress
| Pending | Waiting on action by another party
| Resolved | Resolved pending agreement from customer/sponsor
| Closed | Closed as agreed by customer/sponsor